Actions from Certified Open Conference Call 091007

Application Process	BB, RN to finalise testing, then pass to SC for further test

Web site	GT, SC,GG to review and GT consolidated comments to RN

Docn	SC to incorporate changes to P Ops ( inc logo change)
RN to circ logo update inc ®
All to review both POps and P Framework
RN Sample Certificate be updated

Legal/Governance	BB to take final POps and get quote on Directors Insurance
SC check docs received from GT and return to BB
BB to confirm bank account status
All to suggest names re Gov Council as per categories agreed

Sign Ups	All – further comments re draft letters produced by GT

Launch	Draft plan from Sachiko Muto
Flier to be produced (GT), finalised copy to be with GG by 9 Nov for	IGF

Next Call	Monday 151007 at 1000 UKT 1100 CET
SC to check/advise FSFE call hosting