## KA2_SP_TIMELINE_TEMPLATE
Name of the project: | FOSS4SMEs
PROJECT TIMETABLE
|  | 2017 |  |  | 2018 | [11 empty] | 2019
|  | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep
Project activity* | MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | nov | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
A1
A2
A3
A4 | bar: 2018 dec M15; 2019 aug M23 to 2019 sep M24
A5
A6 | bar: 2019 jul M22 to 2019 sep M24
A7 | bar: 2018 dec M15; 2019 jun M21
A8
A9
A10
A11 | bar: 2019 jan M16; 2019 aug M23 to 2019 sep M24
A12
A13
O1/A1 Research
O1/A2 ECVET profile
O2/A1DevOfContents | bar: 2018 oct M13 to 2018 nov M14
O2/A2 translation | bar: 2018 dec M15
O2/A3 FOSS4SMEs Platform | bar: 2018 nov M14 to 2019 jan M16
O2/A4 Assessment | bar: 2019 feb M17 to 2019 may M20
O2/A5 Final release | bar: 2019 jun M21
O3/A1-ToR-research | bar: 2019 mar M18 to 2019 apr M19
O3/A2 Draft.Consult | bar: 2019 may M20 to 2019 jul M22
O3/A3 Final report | bar: 2019 aug M23
M1 |  | GR
M2 | [7 empty] | DE
M3 | bar: 2018 dec M15
M4 | bar: 2019 sep M24
E1 | bar: 2019 apr M19
E2 | bar: 2019 apr M19
E3 | bar: 2019 apr M19
E4 | bar: 2019 apr M19
E5 | bar: 2019 apr M19
E6 | bar: 2019 sep M24
Please insert rows as needed
*Project activity types:
| An | - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
| On/An | - INTELLECTUAL OUTPUTS/ACTIVITIES
| Mn | - TRANSNATIONAL PROJECT MEETINGS
| En | - MULTIPLIER EVENTS
| Cn | - LEARNING/TEACHING/TRAINING ACTIVITIES
| n | - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.